## Risk register
Project risk register
One risk per row · replace the fictional examples
Open risks |  |  | Score ≥ 15 |  |  | Reviews overdue*
2 |  |  | 1 |  |  | 0
FICTIONAL EXAMPLES
ID | Risk: cause → event → impact | Category | Probability 1–5 | Impact 1–5 | Score P × I | When to check | Owner | Action now | Warning signal | Backup plan if triggered | Status | Next review | Decision / next action
EX-01 | Website copy is awaiting client approval → the client may reply after Thursday noon → Monday’s launch could slip | Client approval | 3 | 4 | 12 | Thursday at noon | Camille, project lead | Send a clear approval request on Tuesday and follow up on Wednesday | No written approval by Thursday noon | Agree a new date or reduced scope with the client; publish only approved copy | Open |  | Get a written response before Thursday noon
EX-02 | Historical data has not been profiled → unexpected formats may fail migration → launch may be delayed | Data | 4 | 4 | 16 | Before trial migration | Data lead | Test a representative sample and agree rejection rules | Over 5% of records rejected in trial | Run a second cleanse and defer non-critical history | Open |  | Set the trial migration date

## How to use
How to use this register
Start with EX-01, then replace the examples with your own risks.
1 Describe | Write the cause, uncertain event and concrete effect on a project objective.
2 Assess | Choose probability and impact from 1 to 5. The score calculates itself; use it to sort, not predict.
3 Respond | Name an owner, an action to take now, a warning signal and a backup plan.
4 Review | Set a review date. Update the score, next action and status at each review.
Simple guide
Probability | 1 = unlikely in the current context; 5 = very plausible soon.
Impact | 1 = minor effect; 5 = threatens a major goal, safety or a mandatory obligation.
Priority | Score 15–25 = discuss first. Escalate impact 5 even if its total score is lower.
Status | “Occurred” means the event happened: manage it as an issue from that point.
The EX rows are fictional. *A review without a date cannot appear overdue. Replace the examples.